UCLA Blum Summer Scholars 2014

Goals of Program

- Send ____ UCLA graduate students to countries throughout Latin America (prioritizing Central America) for field study experiences. Recruit students from a range of disciplines and graduate programs on campus to create diverse learning experiences.

UCLA Schools and Departments for Outreach/Collaboration

- Fielding School of Public Health

- Luskin School of Public Affairs

- Center for World Health

- Latin American Studies

- David Geffen School of Medicine

- Department of Political Science

- School of Nursing

- School of Dentistry

- Department of Education

- School of Law

- Institute of the Environment and Sustainability

- Art and Global Health Center

- International Institute

- Latin American Institute

- Center for Argentina, Chile and the Southern Cone

- Center for Brazilian Studies

- Center for Mexican Studies

- Burkle Center for International Relations

- Program on International Migration

- Anderson School of Management

- Anthropology

- Architecture

- Atmospheric and Ocean Sciences

- Chicana/o Studies

- Civil and Environment Engineering

- Community Health Sciences

- Environmental Health Science

- Department of Film, TV

- Gender Studies

- Health Policy and Management

- Oral Biology

Tentative Timeline

January

- Have application process/timeline set up

- Outreach for potential placements with host organizations: IDB, PAHO, FriendsNE/UNAN, ECOSUR, World Vision International

- Budget (Budget info from last year J:\UCLA Blum Center\Training\UCLA Blum Summer Scholars Program\Field Study in Summer 2013\Blum Graduate Program\Budget)

February

- By beginning of February: finalize placements/commitments of host organizations What specifically will these agreements entail? Will it define (from most general to specific):

1) which specific organization/location?

2)  which specific member (e.g. P.I.) of the organization that the student will work with?

3) which area of research team the student will become a part of? (e.g. a P.I. interested in infectious disease may be interested in multiple disease, will we specify which one)

4) which specific project the applicant will work as a part of?

- Mid-February: distribute call for applicants

- Develop/finalize process and participants for selecting students (selection committee)

- Recruit/finalize UCLA faculty mentors for selected students – (match with appropriate placement sites/orgs?)

March

- Applications due (late March/early April)

- March 22: Center for World Health training (their resources are available online if our students cannot attend)

April

- Applications due (late March/early April)

- Selection and announcement of applicants – early April

- Work with students to develop projects with UCLA mentors/host organizations

- Logistics: support travel arrangements for summer field study, airfare, food, health insurance

- Plan goals for four days of orientation to be held in May and June?? Was in a timeline from last year (last year this entailed info on how to blog, how to present data in final paper (which one of the students did at the end of the summer, I would imagine the other student did as well but worked on it back in US)

May

- Refine projects

- Continue logistics support

- Blum Center Summer Scholars Orientation?

June

- Blum Center Summer Scholars Orientation?

(last year’s timeline):

Summer Field Study

The purpose of this field study component is to raise the students’ awareness of health inequities and of the pervasive impact these inequities have on communities.  The summer field study experience will spark student interest in social justice and how political agendas influence the nature and treatment of human rights. The summer field study will be a 2-3 week experience on a site in Los Angeles and in Latin America during the summer of 2013.

November 2012: collaborate with cluster team on ideas for summer field study in Los Angeles and another site in Latin America, contact each of the suggested organizations to find out feasibility

December 2012: present organizations and their feasibility to cluster faculty and get feedback, make final decision on organizations in Los Angeles and Latin America, create budget and calendar for summer field study time frame

January 2013: confirm budget and time frame with selected organizations in Los Angeles and Latin America, set deadline for applications, create flyer to advertise, present to students

February 2013: gather applications from students, begin interviewing prospective students

March 2013: interview prospective students, decide on final candidates with cluster team, confirm final participants in summer field study

April 2013: make travel arrangements for summer field study, airfare, food, health insurance, plan goals for four days of orientation to be held in May and June

May2013: hold one or two sessions of orientation for summer field study participants

June 2013: hold one or two sessions of orientation for summer field study participants

July 2013: Begin Summer field study, graduate student that accompanies them will continue to check in on student progress and encourage students

August 2013: End Summer field study and hold summer review session, work with students on presenting their findings, hold workshop to help them structure their findings